## excel (2)
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
After you use the PROBE Wizard to produce an overall time estimate, you have the opportunity to distribute that time across the phases listed in the "Time in Phase" section of the Project Plan Summary. Unfortunately, the times that you have entered for the phases do not add up to the total time estimate you created with PROBE. Please check your time in phase estimates and make the necessary corrections.
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 19.5 | 16.9 | 27.9
Planned Time | 0.51597 |  | 0.82847
Actual Tiempo |  | 0.60903 | 0.97986
CPI (Cost-Performance Index) |  |  | 0.85
% Reuse | 2.56% | 3.14% | 2.88%
% New Reusable | 13.3% | 23.5% | 8.85%
Test Defects/KLOC or equivalent | 0 | 4.05 | 1.53
Total Defects/KLOC or equivalent | 19.6 | 8.1 | 15.3
Yield % | 71.7% | 50% | 80%
Code Review Rate | 1447 | 780 | 2068
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 21:22 el 06-mar-2017